## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| SOEN SOLUTIONS | Jake Lamothe | 2021-01-22 | 2021-04-20 |  | 40% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 3 |  |  | 32 | 2021-02-25 | 2021-03-17 | 20 | Not Started
| Item Creation | Epic | TBD | 8 | 2021-02-25 | 2021-03-03 | 6 | Not Started
| Implement the ability to define end-product items that are to be sold. | Task | TBD | 2 | 2021-02-25 | 2021-02-27 | 2 | Not Started
| Implement the ability to define intermediate items used in the production of other items. | Task | TBD | 2 | 2021-02-27 | 2021-03-01 | 2 | Not Started
| Implement the ability to define item variants | Task | TBD | 2 | 2021-03-01 | 2021-03-02 | 1 | Not Started
| Implement the ability to export the list of the created items. | Task | TBD | 2 | 2021-03-02 | 2021-03-03 | 1 | Not Started
| Operations Location Set Up | Epic | TBD | 7 | 2021-03-03 | 2021-03-07 | 4 | Not Started
| Implement modification of inventory | Task | TBD | 3 | 2021-03-03 | 2021-03-06 | 3 | Not Started
| Implement visualization of inventory | Task | TBD | 2 | 2021-03-03 | 2021-03-06 | 3 | Not Started
| Implement definition of a location's charcatericstics | Task | TBD | 2 | 2021-03-06 | 2021-03-07 | 1 | Not Started
| Production Chain Management | Epic | TBD | 9 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement production rate set up | Task | TBD | 3 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement transfer between location | Task | TBD | 2 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement the ability to set up inventory change rules | Task | TBD | 4 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Sales Management | Epic | TBD | 8 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement quotes generation | Task | TBD | 3 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement the set up for end-product orders | Task | TBD | 3 | 2021-03-07 | 2021-03-17 | 10 | Not Started
| Implement logs and reports generation | Task | TBD | 2 | 2021-03-07 | 2021-03-17 | 10 | Not Started