## Sheet1
Defects tracking Report Srpint 1&2
(done by issue #)
| bug type | location | found by | estimated man hours | id | status | found on | last checked
| functional | api/src/routes/users/register-business | christian | 2 | 40 | fixed and merged | 2021-02-20 | 2021-02-23
| non-functional | app/src/App.tsx | christian | 1 | 47 | ongoing | 2021-02-24 | 2021-02-24
| non-functional | app/src/helpers/theme.ts | christian | 4 | 46 | ongoing | 2021-02-24 | 2021-02-24
Defects tracking Report Srpint 3