## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE | Sprint 4
| SOEN SOLUTIONS | Jake Lamothe | 2021-04-03 | 2021-04-07 |  | 0% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
|  |  |  | 21 | 2021-03-18 | 2021-04-07 | 20 | Not Started
| Smaller functionality | Epic | TBD | 5 | 2021-04-03 | 2021-04-07 | 4 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/60
| export different tables to csv | task | TBD | 2 | 2021-04-03 | 2021-04-06 | 3 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/57
| email to specific roles (e.g. shipment sends email to local warehouse manager) | task | TBD | 2 | 2021-04-03 | 2021-04-06 | 3 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/58
| mobile frendly | task | TBD | 1 | 2021-04-03 | 2021-04-04 | 1 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/59
| Production Chain Management | Epic | TBD | 9 | 2021-03-20 | 2021-03-27 | 7 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/26
| Implement production rate set up | Task | TBD | 1 | 2021-03-20 | 2021-03-22 | 2 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/25
| Implement transfer between location | Task | TBD | 3 | 2021-03-20 | 2021-03-24 | 4 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/24
| Implement the ability to set up inventory change rules | Task | TBD | 5 | 2021-03-20 | 2021-03-27 | 7 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/23
| Sales Management | Epic | TBD | 7 | 2021-03-27 | 2021-04-03 | 7 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/21
| Implement quotes generation | Task | TBD | 1 | 2021-03-27 | 2021-03-29 | 2 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/14
| Implement the set up for end-product orders | Task | TBD | 1 | 2021-03-27 | 2021-03-29 | 2 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/16
| Implement logs and reports generation and transaction history | Task | TBD | 5 | 2021-03-27 | 2021-04-03 | 7 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/17