## Agile Project Plan
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| SOEN SOLUTIONS | Jake Lamothe | 2021-04-08 | 2021-04-20 |  | 0% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 5 |  |  | 16 | 2021-04-08 | 2021-04-19 | 11 | Not Started
| front-end | Epic | TBD | 9 | 2021-04-08 | 2021-04-16 | 8 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/71
| production rate(front end) | Task | TBD | 5 | 2021-04-08 | 2021-04-16 | 8 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/69
| shipments | Task | TBD | 4 | 2021-04-08 | 2021-04-14 | 6 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/70
| small features | Epic | TBD | 7 | 2021-04-16 | 2021-04-19 | 3 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/76
| scheduling/events | Task | TBD | 3 | 2021-04-16 | 2021-04-19 | 3 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/72
| enforce user permissions | Task | TBD | 1 | 2021-04-16 | 2021-04-19 | 3 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/73
| link employees to locations | Task | TBD | 2 | 2021-04-16 | 2021-04-18 | 2 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/74
| export to csv | Task | TBD | 1 | 2021-04-08 | 2021-04-10 | 2 | Not Started | https://app.zenhub.com/workspaces/bike-erp-60107a1f4371240015bce41c/issues/redknight990/soen-solutions/75